## UAT Summary
Enterprise Reporting Modernization - UAT
Execution dashboard ¦ Update Actual Result, Status, Defect ID, and Evidence in Test Cases
Total Tests | Executed | Passed | Failed | Blocked | Pending | Pass Rate | UAT Gate
18 | 17 | 15 | 0 | 2 | 1 | 88.24% | NOT READY
Status | Count | Share | Interpretation
Pass | 15 | 83.33% | Meets expected result
Fail | 0 | 0% | Does not meet expected result
Blocked | 2 | 11.11% | Cannot execute due to dependency
Not Run | 1 | 5.556% | Pending execution
Exit Criteria | Target | Current | Result | Owner | Evidence | Decision Date | Comment
Must-have tests executed | 100% | 94.12% | Fail | UAT Lead | Test Cases
Overall pass rate | >=95% | 88.24% | Fail | UAT Lead | UAT Summary
Open Sev 1/2 defects | 0 | 1 | Fail | Product Owner | Defects
Business approvals | 3 | 2 | Fail | BA | Sign-Off

## Test Cases
UAT Test Cases
Traceable functional, KPI, control, security, performance, and accessibility tests
Test ID | Req ID | Type | Priority | Scenario | Precondition | Test Steps | Expected Result | Actual Result | Tester | Exec Date | Status | Defect ID | Evidence / Notes
UAT-01 | FR-01 / KPI-03 | KPI | Must | Net Revenue calculation | Approved invoice/credit dataset | Filter Jan 2026; compare line and total | Gross - discounts - approved credits; exact to $0.01 | Matches expected control total | Finance Tester | 2026-09-14 | Pass |  | Recon!A7:H10
UAT-02 | BR-03 / DQ-02 | Data Quality | Must | Duplicate survivor | Duplicate key with newer modified timestamp | Refresh; inspect accepted and quarantine sets | One latest valid survivor; conflict logged | Latest valid row retained | Data Steward | 2026-09-14 | Pass |  | Batch B20260914
UAT-03 | BR-04 / DQ-08 | Mapping | Must | Effective-dated department | Alias spans reorganization date | Test dates before and after effective change | Exactly one department resolves for each date | Historical mapping preserved | Data Steward | 2026-09-14 | Pass |  | Mapping v1.2
UAT-04 | KPI-05 | KPI | Must | On-time boundary | Delivered on promised date | Filter boundary record | Counts as on time | Included in numerator | Ops Tester | 2026-09-15 | Pass |  | Order O-1008
UAT-05 | KPI-06 | KPI | Must | Fill rate cap | Shipped quantity exceeds ordered by one | Review line and aggregate | Line numerator capped at ordered quantity | 100%; not 105% | Ops Tester | 2026-09-15 | Pass |  | Order O-1011
UAT-06 | KPI-07 | KPI | Must | Zero denominator return rate | No shipped units in selected slice | Apply filter | Returns blank, not 0 or error | Blank displayed | Ops Tester | 2026-09-15 | Pass |  | Screenshot OPS-06
UAT-07 | BR-10 / DQ-06 | Reconciliation | Must | Ledger tolerance | Load control total and mart total | Run control | Pass only within both 0.5% and $1,000 | Within both thresholds | Finance Tester | 2026-09-15 | Pass |  | Recon!A7:H10
UAT-08 | FR-02 | Functional | Must | Cross-filtering | Dashboard refreshed | Select East and Product A | All visuals and cards reflect filters | Cross-filter verified | Business Tester | 2026-09-16 | Pass |  | Screenshot EX-08
UAT-09 | FR-02 | Functional | Must | 13-month trend | 13 months loaded | Review axis and totals | Chronological 13 months; no gaps | 13 months shown | Business Tester | 2026-09-16 | Pass |  | Screenshot EX-09
UAT-10 | FR-03 / US-05 | Lineage | Must | Order-line drill-through | Select a variance point | Open detail and metadata | Source file, key, batch, load time visible | Trace complete | Audit Tester | 2026-09-16 | Pass |  | Screenshot LN-10
UAT-11 | FR-04 | Control | Must | Certification banner | Force failed reconciliation | Refresh report | Banner = Not Certified and link shows failure | Control displayed | BI Tester | 2026-09-16 | Pass |  | Screenshot DQ-11
UAT-12 | DQ-01 | Data Quality | Must | Mandatory field rejection | Null OrderID in landing row | Run validation | Row rejected with DQ-01 and owner | Exception logged | Data Steward | 2026-09-16 | Pass |  | Exception E-12
UAT-13 | NFR-02 | Refresh | Must | Refresh SLA | Scheduled production-like environment | Observe BD2 run | Refresh complete by 9:00 a.m. ET | Awaiting scheduled run | BI Tester |  | Not Run |  | Environment dependency
UAT-14 | NFR-03 / US-06 | Security | Must | East region RLS | East manager test account | Open report and attempt URL/filter changes | Only East rows visible | Awaiting tenant role | Security Tester |  | Blocked | DEF-001 | Tenant role pending
UAT-15 | NFR-03 / US-06 | Security | Must | No unauthorized export | East manager test account | Export detail after filter manipulation | No West rows exported | Awaiting tenant role | Security Tester |  | Blocked | DEF-001 | Tenant role pending
UAT-16 | NFR-01 | Performance | Should | Interaction response | Production-size dataset | Run five standard interactions | 95% complete in <=5 sec | 4.2 sec P95 | BI Tester | 2026-09-17 | Pass |  | Perf log P-16
UAT-17 | FR-06 | Accessibility | Must | Keyboard navigation | Published report | Navigate pages and controls without mouse | Logical tab order and visible focus | Focus order corrected | Accessibility Tester | 2026-09-17 | Pass |  | A11Y checklist
UAT-18 | FR-06 | Accessibility | Must | Contrast and alt text | Published report | Inspect visuals and screen reader labels | Meets contrast; meaningful alt text | Verified | Accessibility Tester | 2026-09-17 | Pass |  | A11Y checklist

## Reconciliation
Reconciliation Controls
Source-to-mart-to-dashboard control totals; thresholds require both percent and absolute variance
Period | Control | Source Total | Mart Total | Dashboard Total | Variance $ | Variance % | Tolerance $ | Tolerance % | Result
2026-01-31 | Net Revenue | 985000 | 984600 | 984600 | -400 | -0.04061% | 1000 | 0.5% | Pass
2026-02-28 | Net Revenue | 1018000 | 1018000 | 1018000 | 0 | 0% | 1000 | 0.5% | Pass
2026-03-31 | Net Revenue | 1062500 | 1062300 | 1062300 | -200 | -0.01882% | 1000 | 0.5% | Pass
2026-03-31 | COGS | 662000 | 662000 | 662000 | 0 | 0% | 1000 | 0.5% | Pass

## Quality Analysis
Data Quality Analytical Controls
Deterministic thresholds and rolling statistical signals for certified reporting batches
Period | Landed Rows | Accepted Rows | Missing Mandatory | Duplicate Rows | Unmapped Rows | Completeness % | Duplicate % | Mapping Success % | Revenue $ | Revenue z-score
2025-04-30 | 48210 | 48170 | 12 | 18 | 10 | 99.98% | 0.03734% | 99.98% | 880000
2025-05-31 | 49120 | 49079 | 14 | 16 | 11 | 99.97% | 0.03257% | 99.98% | 895000
2025-06-30 | 50340 | 50296 | 15 | 17 | 12 | 99.97% | 0.03377% | 99.98% | 910000
2025-07-31 | 51440 | 51397 | 13 | 19 | 11 | 99.97% | 0.03694% | 99.98% | 925000
2025-08-31 | 52210 | 52169 | 14 | 17 | 10 | 99.97% | 0.03256% | 99.98% | 938000
2025-09-30 | 53180 | 53140 | 11 | 18 | 11 | 99.98% | 0.03385% | 99.98% | 947000
2025-10-31 | 54620 | 54577 | 15 | 17 | 11 | 99.97% | 0.03112% | 99.98% | 962000
2025-11-30 | 55810 | 55770 | 12 | 18 | 10 | 99.98% | 0.03225% | 99.98% | 970000
2025-12-31 | 57120 | 57078 | 14 | 19 | 9 | 99.98% | 0.03326% | 99.98% | 985000
2026-01-31 | 58450 | 58402 | 16 | 20 | 12 | 99.97% | 0.03422% | 99.98% | 984600
2026-02-28 | 59210 | 59165 | 14 | 19 | 12 | 99.98% | 0.03209% | 99.98% | 1018000
2026-03-31 | 60780 | 60620 | 62 | 71 | 27 | 99.9% | 0.1168% | 99.96% | 1062300 | 2.7396

## Traceability
Requirements Traceability Matrix
Bidirectional linkage from business need through design, implementation, test, defect, and approval
Requirement | Business Objective | KPI / Rule | Design Component | User Story | UAT Test | Defect | Approval Owner | Coverage
FR-01 | Standardize executive reporting | KPI-03/05/06/08/09 | Executive Summary | US-01/02 | UAT-01/04/05/07 |  | BI Product Owner | Complete
FR-02 | Enable multidimensional analysis | All KPIs | Conformed dimensions | US-02/03 | UAT-08/09 |  | BI Product Owner | Complete
FR-03 | Make results auditable | BR-02; DQ-10 | Lineage drill-through | US-05 | UAT-10 |  | Internal Audit | Complete
FR-04 | Expose reporting trust | DQ-01 to DQ-10 | Data Quality page | US-04/07 | UAT-11/12 |  | Reporting Manager | Complete
NFR-01 | Maintain user productivity | Performance SLA | Aggregations/incremental refresh | US-07 | UAT-16 |  | BI Product Owner | Complete
NFR-02 | Accelerate close | DQ-05 | Refresh orchestration | US-07 | UAT-13 |  | Reporting Manager | Complete
NFR-03 | Protect regional data | RLS rule | User-region bridge | US-06 | UAT-14/15 | DEF-001 | Security Owner | Complete
NFR-04 | Preserve evidence | Retention rule | Landing/audit store | US-05 | UAT-10 |  | Data Owner | Complete
NFR-05 | Provide dependable access | Availability SLA | Service monitoring | US-07 | UAT-13 |  | BI Product Owner | Complete

## Benefits Case
Benefits Realization Model
Illustrative planning assumptions; replace with approved finance inputs before funding approval
Benefit Driver | Baseline Hours / Month | Target Hours / Month | Hours Released / Month | Annual Hours | Blended Rate | Annual Capacity Value
Reporting analyst effort | 80 | 24 | 56 | 672 | 65 | 43680
Manager review effort | 30 | 12 | 18 | 216 | 65 | 14040
Defect rework | 20 | 5 | 15 | 180 | 65 | 11700
Financial Summary | Value
Annual capacity value | 69420
Implementation + year-one operating cost | 54000
First-year net benefit | 15420
Benefit-cost ratio | 1.2856
Payback months | 9.3345

## Defects
UAT Defect Log
Severity: 1 Critical, 2 High, 3 Medium, 4 Low
Defect ID | Test ID | Summary | Severity | Owner | Opened | Target Fix | Status | Retest Result | Notes
DEF-001 | UAT-14 / 15 | RLS tenant role not provisioned | 2 | Security Admin | 2026-09-16 | 2026-09-21 | In Progress | Not Retested | Blocks security exit tests
DEF-002 | UAT-17 | Initial focus order skipped certification banner | 3 | BI Developer | 2026-09-17 | 2026-09-17 | Closed | Pass | Corrected and retested

## Sign-Off
UAT Sign-Off
Approval is recorded after exit criteria are met and evidence is reviewed
Role | Approver | Area | Decision | Decision Date | Conditions | Signature / Evidence Ref
Corporate Controller | A. Patel | Finance KPIs & reconciliation | Pending |  | Security tests must pass
Operations Director | M. Chen | Operations KPIs | Approved | 2026-09-18 | None | Email approval OPS-18
BI Product Owner | J. Rivera | Dashboard & operations | Pending |  | Close DEF-001
Data Steward | S. Brooks | Mappings & data quality | Approved | 2026-09-18 | None | Confluence decision DQ-42